## Sprint 3
Sprint 3 - Day 1
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Excecutive Summary - Kaitlin | 3 | UML Class - Somya, Nishant | 8
UML Package Diagram - Somya | 8 | Security Plan - Kaitlin | 5
UML Deployment Diagram - Nishant, Amit | 8 | Sequence Diagram: Dispatch - Amrutha, Praveen | 3
YouTube Video Upload - Praveen, Somya | 2 | Sequence Diagram: Record Patient - Mihir | 3
Sequence Diagram: EMT Shifts - Praveen, Amrutha | 3 | Sequence Diagram: Log calls - Amit, Mihir | 3
Sequence Diagram: Waiting Calls - Amit, Mihir | 3
Sprint 3 - Day 2
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
UML Package Diagram - Somya | 8 | UML Class - Somya, Nishant | 8 | Sequence Diagram: Log calls - Amit, Mihir | 3
UML Deployment Diagram - Nishant, Amit | 8 | Security Plan - Kaitlin | 5 | Sequence Diagram: Record Patient - Mihir | 3
YouTube Video Upload - Praveen, Somya | 2 | Sequence Diagram: Dispatch - Amrutha, Praveen | 3
Sequence Diagram: EMT Shifts - Praveen, Amrutha | 3 | Excecutive Summary - Kaitlin | 3
|  | Sequence Diagram: Waiting Calls - Amit, Mihir | 3
Sprint 3 - Day 3
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
YouTube Video Upload - Praveen, Somya | 2 | Security Plan - Kaitlin | 5 | UML Class - Somya, Nishant | 8 | Sequence Diagram: Log calls - Amit, Mihir | 3
|  | UML Package Diagram - Somya | 8 | Excecutive Summary - Kaitlin | 3 | Sequence Diagram: Record Patient - Mihir | 3
|  | Sequence Diagram: EMT Shifts - Praveen, Amrutha | 3 | Sequence Diagram: Waiting Calls - Amit, Mihir | 3
|  | UML Deployment Diagram - Nishant, Amit | 8 | Sequence Diagram: Dispatch - Amrutha, Praveen | 3
Sprint 3 - Day 4
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
YouTube Video Upload - Praveen, Somya | 2 | UML Deployment Diagram - Nishant, Amit | 8 | Sequence Diagram: Dispatch - Amrutha, Praveen | 3 | Sequence Diagram: Log calls - Amit, Mihir | 3
|  | UML Package Diagram - Somya | 8 | Sequence Diagram: EMT Shifts - Praveen, Amrutha | 3 | Sequence Diagram: Record Patient - Mihir | 3
|  |  |  | Security Plan - Kaitlin | 5 | Sequence Diagram: Waiting Calls - Amit, Mihir | 3
[6 empty] | Excecutive Summary - Kaitlin | 3
[6 empty] | UML Class - Somya, Nishant | 8

## Sprint 2
Sprint 2 - Day 1
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Physical ERD | 5 | Logical ERD | 8
Enhance DFD Level 0 | 3 | Create DFD Level 1 (EPCR) | 3
Create DFD Level 1 (CAD) | 3 | Acceptance Criteria (10 user stories) | 8
Create DFD Level 1 (BSMS) | 3 | Context Level DFD | 2
Testing Plan to Measure Acceptance Criteria | 5
Create DFD Level 1 (SMS) | 3
Enhance Case User Stories | 1
Upload Standup to YouTube | 2
Sprint 2 - Day 2
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Physical ERD - Nishant | 5 | Acceptance Criteria (10 user stories) - Amrutha, Praveen, Mihir | 8 | Create DFD Level 1 (EPCR) - Nishant | 3
Testing Plan to Measure Acceptance Criteria -Amrutha, Praveen, Mihir | 5 | Create DFD Level 1 (SMS) - Nishant | 3 | Logical ERD - Kaitlin, Somya | 8
Enhance Case User Stories | 1 | Create DFD Level 1 (CAD) - Kaitlin, Somya | 3 | Context Level DFD - Amit | 2
Upload Standup to YouTube | 2 | Create DFD Level 1 (BSMS) - Praveen (But now Amit) | 3
Enhance DFD Level 0 | 3
Sprint 2 - Day 3
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Enhance Case User Stories | 1 | Physical ERD - Nishant | 5 | Create DFD Level 1 (SMS) - Nishant | 3 | Create DFD Level 1 (EPCR) - Nishant | 3
Upload Standup to YouTube | 2 | Testing Plan to Measure Acceptance Criteria -Amrutha, Praveen, Mihir | 5 | Create DFD Level 1 (CAD) - Kaitlin, Somya | 3 | Logical ERD - Kaitlin, Somya | 8
Enhance DFD Level 0 | 3 |  |  | Create DFD Level 1 (BSMS) - Praveen (But now Amit) | 3 | Context Level DFD - Amit | 2
|  |  |  | Acceptance Criteria (10 user stories) - Amrutha, Praveen, Mihir | 8
Sprint 2 - Day 4
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Upload Standup to YouTube | 2 | Enhance Case User Stories | 1 | Physical ERD - Nishant | 5 | Create DFD Level 1 (EPCR) - Nishant | 3
|  | Enhance DFD Level 0 | 3 | Testing Plan to Measure Acceptance Criteria -Amrutha, Praveen, Mihir | 5 | Logical ERD - Kaitlin, Somya | 8
[6 empty] | Context Level DFD - Amit | 2
[6 empty] | Acceptance Criteria (10 user stories) - Amrutha, Praveen, Mihir | 8
[6 empty] | Create DFD Level 1 (SMS) - Nishant | 3
[6 empty] | Create DFD Level 1 (CAD) - Kaitlin, Somya | 3
[6 empty] | Create DFD Level 1 (BSMS) - Praveen (But now Amit) | 3

## Sprint 1
Sprint 1 - Day 1
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Create DFD Level 0 | 8
Upload Standup video on YouTube | 1
Create Cover Page | 3
Create Case User Stories | 5
Gather Case Requirements | 1
Create YouTube channel | 3
Read Rescue 911 Case | 1
Total Effort Points | 22
Sprint 1 - Day 2
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Create DFD Level 0 | 8 | Create Case User Stories | 5 | Create Cover Page | 3 |  |  | Create YouTube channel | 3
Upload Standup video on YouTube | 1 | Gather Case Requirements | 1 |  |  |  |  | Read Rescue 911 Case | 1
Sprint 1 - Day 3
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Upload Standup video on YouTube | 1 | Create DFD Level 0 | 8 | Create Case User Stories | 5 | Create Cover Page | 3 | Create YouTube channel | 3
[8 empty] | Read Rescue 911 Case | 1
[8 empty] | Gather Case Requirements | 1
Sprint 1 - Day 4
To Do | Effort | In Progress | Effort | QA | Effort | In Demo | Effort | Done | Effort
Upload Standup video on YouTube | 1 |  |  | Create DFD Level 0 | 8 | Create Cover Page | 3 | Create YouTube channel | 3
[6 empty] | Create Case User Stories | 5 | Read Rescue 911 Case | 1
[8 empty] | Gather Case Requirements | 1